Elizabeth Parker (B), (C)

Case Analysis

Summary

Elizabeth Parker obtains lateral transfer to agency facing 1 year deadline for inspections of 250 towns. The civil servants under her command are accomplishing nothing, and she must find a way to meet the deadline.

Issues

- The directors were doing nothing

- Most of the inspectors did not understand the task, and some were faking it (perhaps in over their heads)

- Task was pretty overwhelming

- Civil servants are difficult to fire

Analysis

- Start by working with existing structure and adopt other solutions only as needed

  - Avoids immune reaction

- Begin working on the understanding and buy-in issues by instituting group meetings to discuss

  - This failed because no history/culture of doing this – too novel; situation too far gone

- Begin to force directors to do more by giving them specific responsibilities – supervising the inspectors

  - This failed too

- Unlike case (A), the project could at best avoid failure. In A, project completion meant net gain for department. In B, project completion meant avoiding failure.

- She began to bring in new personnel a little at a time. First thing is new supervisor, called a “project manager”, to get around the do-nothing directors.

- She addressed the ignorance problem by instituting training sessions using U of Delaware people, writing written manuals

- She made task less overwhelming by taking over the scheduling for the inspectors. This also served to reduce ability to fake it and be accountable

- She introduced fear of failure by having inspectors present to the Secy of Environmental Affairs

- Helped inspectors by getting firms to cooperate

- She made “her” inspectors the majority

- New people were trained by the good inspectors, ending the cycle of bad socialization

Key Lessons

- Formalization & scientific management were helpful to impose order and enable low level personnel to get things done.

- Made much more use of authority than in A, but mostly it was borrowed from her boss

- It is not enough to specify worker outputs. To get results need to specify work process

- If dependent on those who are resisting you, reduce dependence on some, and control the others. Resource-Dependence theory.

- Choose big tasks from which you will emerge with respect and power

- At the end, she promotes people, making them indebted to her

- She builds the identification kind of power (see Kotter)

Discussion Questions

- Is this case about how you get power? Or how you use power to get things done?

  - She made use of authority several times

  - She slowly infiltrated her people

  - She probably gained a huge amount of respect for completing this in time

- Who was she dependent on, and why?

  - Boss for his authority, inspectors for their labor

- How did she reduce her dependency on the directors and inspectors?

- How does she manage her dependency on boss?

  - Protecting from enemies

  - Doing a good job

- What did Dempsey accomplish?

  - Opting out (like Nick on The Apprentice) meant he became dispensable – others reduced dependence on him, so his power was reduced

  - Failed to gain from this. Can’t call on Elizabeth in the future to accomplish things.

- Kotter’s thesis is that managers need power to manage. Is Elizabeth Parker a case in point?

- Knowledge of the network was key in A and visible in B when she brought in Jensen (knowing who knows what)

- In Kotter’s terms, what is the basis of her power?